November 22, 2022

FACILITIES: Projects under consideration

- Hort Field Lab – swipe card access at west ADA entry; estimate received by F&S and on-hold for funding.

- Hort Field Lab – Clearing out of Room 6 – Room 6 has antique equipment, along with seeds and is rodent/pest issue. Review of space and equipment needs done to clear space and prevent further rodent/pests

- Main Library Exterior Renovations Phase 2C – South Light Court & 1962 NW Addition – Window replacement and masonry repair.  Project placed on the Facilities Planning Committee project list for FY20.

- Main Library Mural Restoration/Cleaning – Follow-up required on mural cleaning

FACILITIES: Projects in Planning

- Grainger Engineering Library – Second Floor Wood Floor. Library Facilities and Grainger Library are reviewing options.  Currently on hold.

- Grainger Engineering Library – 1st floor terrazzo – strip/wax floor, working to schedule. Delayed due to lack of BSW flooring crew.

- Grainger Engineering Library –looking at reviewing HVAC requirements/loads for Room 59 testing center. This may be included with a Retro Cx HVAC upgrade at Grainger.  Working with F&S for further HVAC investigation.

- Main Library Roof and HVAC Exterior Ductwork Replacement – project scope approved and selection of A/E in-progress; anticipate A/E under contract January 2023 with construction starting August 2023.

- MPAL Feasibility Study – Project planning to be initiated June 2022.  Potential scope of work to include, lighting upgrade, flooring replacement, rearrange shelving, ceiling replacement, ADA entry, and painting. A/E under contract November 2022.

- Math Library – Altgeld Hall Remodeling – Construction Documents completed, project scheduled for Fall 2024 in line with Illini Hall completion.

- Oak Street Library Facility - Conservation Lab Humidification – Install humidification in the existing HVAC system – F&S is putting together estimates.

- Ricker Library – power distribution in east wing for computers, scanning, and collaboration tables.  Estimate received by F&S and under review.

- Undergraduate Library – redevelopment project to turn UGL into the Archives and Special Collections Building; Construction Documents at 50% with Construction Manager being under contract December 2022. Demolition has started and bidding/award scheduled for mid-Spring 2023 with construction starting around June 2023.

FACILITIES: Projects in Construction

- Main Library - Reading Room 200 Renovation – closed loop radiator system installed; punchlist complete, commissioning of system to be complete mid-December 2022 with project closeout end-December 2022.

- Main Library – F&S – North, South & East Stairway “renovation” – stair tread cleaning – F&S funding approved. F&S Building Services Workers – Flooring Crew will be reviewing the lack of progress with the University Library. Due to COVID, this was delayed. Following up with BSWs to determine when it will be scheduled.

FACILITIES: Projects Completed

- ACES – 3rd and 4th floor east corners cleared out and additional seating added to accommodate UGL closing.

- ACES – Classroom 509 construction completed; open for classes Fall 2022

- Undergraduate Library – all services have been relocated to Grainger, Main, and ACES; demolition has started, refer to UGL Redevelopment Project for further updates.